## Feasibility Analysis
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Rooms may be booked using emails, paper calendars, or spreadsheets; availability may not be updated instantly. | A web-based booking system with a database can show room availability, prevent overlapping bookings, and store reservations securely. | Technically feasible
Operational | Manual coordination takes time; users may not know which rooms are free; double bookings and missed updates can occur. | Employees can search available rooms, create or cancel bookings, and receive confirmations; administrators manage rooms and reservations. | Operationally feasible
Economic | Initial development, hosting, setup, training, and maintenance require a budget. | A simple in-house system can reduce administrative effort, avoid booking conflicts, and improve room utilization. | Economically feasible
Legal | The system stores employee names, contact details, and meeting schedules, which should be protected. | Use authorized accounts, role-based access, secure passwords, and a clear data-retention policy; avoid storing unnecessary personal data. | Legally feasible with safeguards
Schedule | Manual booking workflows cause delays when checking availability and confirming reservations. | A student-project prototype can be planned across requirements, design, development, testing, and deployment in about 6–8 weeks. | Achievable for a prototype

## Cost-Benefit Analysis
Cost–Benefit Analysis – Meeting Room Booking System
Category | Description | Estimated Cost (USD) | Benefits | Estimated Value (per year)
Software / Development | Student prototype developed in-house; database and booking features. | $0–$500 | Automates room searches and reservations; reduces manual coordination. | $1,200 estimated staff time saved
Hosting / Domain | Basic hosting and domain, or university-hosted server. | $100–$250 | Makes booking information accessible online. | $400 saved in coordination time
Setup / Hardware | Uses existing computers and phones; no special hardware required. | $0–$200 | Avoids purchasing dedicated booking equipment. | $200 avoided equipment cost
Training | Short training session for administrators and employees. | $100–$200 | Helps users adopt the system quickly and reduces booking errors. | $500 estimated time saved
Maintenance | Annual updates, backups, and basic technical support. | $150–$300 / year | Keeps room availability and booking records reliable. | $600 avoided rework / disruption
Administration | Current manual coordination through emails, messages, or spreadsheets. | $300–$600 / year (current effort) | Less time spent checking calendars and resolving booking conflicts. | $900 estimated staff time saved
Summary
Estimated Initial Costs: $200–$1,150
Estimated Annual Benefits / Savings: about $2,600
Indicative Payback Period: within 1 year, if estimated time savings are achieved
Conclusion: The project appears economically feasible as a low-cost prototype. Figures are illustrative estimates and should be adjusted to the university's actual costs and scale.

## Assumptions
Assumptions and Notes
Project: Meeting Room Booking System (Project 101)
Sponsor: University Administration / Facilities Management
Currency: USD, matching the supplied template.
All cost and benefit figures are illustrative estimates for academic feasibility analysis, not vendor quotes.
Assumes existing computers and internet are available; no dedicated hardware or paid enterprise software is required for the prototype.
Annual benefits represent estimated staff time saved and avoided booking conflicts; actual savings depend on the number of rooms and users.
Legal feasibility assumes the university approves data handling, access permissions, and retention practices.