## Feasibility Study
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Manual tracking of office assets; delays in auditing; risk of asset loss; no real-time availability status. | Web/desktop system with a central database (MySQL/PostgreSQL); barcode/QR code scanners for quick tracking; real-time dashboard. | ✅ Technically feasible
Operational | Manual asset allocation is time-consuming; employee frustration over missing equipment; complex tracking across departments. | Faster asset checkout/return; automated return reminders; clear accountability; reduced administrative workload; seamless employee onboarding. | ✅ Operationally feasible
Economic | High costs from lost or misplaced equipment; administrative overhead for spreadsheet management; cost of software/hardware implementation. | Drastically reduces asset replacement costs; eliminates paper/manual tracking expenses; lower administrative costs; improved long-term asset lifecycle management. | ✅ Cost-effective
Legal | Need compliance with data privacy regulations (employee data) and corporate asset security policies. | Implement encrypted data storage; role-based access control (RBAC); strict compliance with organizational compliance policies. | ✅ Legally feasible
Schedule | Asset audits and manual recovery take months and disrupt active company operations. | Estimated project implementation timeline of 3–5 months (requirements alignment → development → testing → deployment). | ✅ Achievable timeline
Cost–Benefit Analysis – Office Asset Checkout System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | Development of the Asset Checkout platform or software license subscription | $1,500 – $4,000 | Centralized tracking reduces equipment hoarding and manual logging errors. | $2,500 savings in administrative overhead
Hardware | QR code/Barcode scanners, asset tags/labels, and secure hosting infrastructure | $1,000 – $2,500 | Instant check-in/out through physical tags; reduced manual audit time. | $2,000 saved in hardware loss and tracking time
Training | IT staff and general employee training sessions on using the system | $300 – $700 | Smooth transition, high system adoption rate, and fewer user errors. | Increased operational productivity (~$1,000)
Maintenance | Annual cloud hosting, technical support, security patches, and upgrades | $600 – $1,200 | Guarantees high system uptime, secure data backups, and asset protection. | $1,500 saved by preventing downtime/auditing gaps
Administration | Current spreadsheet/paper-based asset tracking methods | $1,000 annually | Fully eliminated with the automated software platform. | $1,000 saved directly from labor shift
## Summary
Total Estimated Costs (first year): $3,400 – $8,400
Total Estimated Annual Benefits/Savings: $6,500 – $7,000+
Payback Period: Within 1 to 1.5 years
Conclusion: The Office Asset Checkout and Return System is economically feasible with clear resource optimization.