## ورقة1
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Manual maintenance requests through calls, messages, or paper; delays; lost requests; no real-time status tracking. | Web/desktop system with centralized database (MySQL/PostgreSQL); online request submission; status tracking; staff assignment; cloud backup. | ✅ Technically feasible
Operational | Manual follow-up is time-consuming; difficulty tracking open maintenance requests; tenants may not know request status. | Faster request handling; automatic status updates; easy tracking; reduced administrative workload; better tenant satisfaction. | ✅ Operationally feasible
Economic | Cost of software, hardware/hosting, training, and maintenance. | Saves administrative time; reduces lost requests and repeated follow-ups; improves maintenance efficiency and resource utilization. | ✅ Cost-effective
Legal | Need to protect tenant contact details, property information, and maintenance records. | Implement access control, secure authentication, data protection and privacy policies; restrict access to authorized users. | ✅ Legally feasible
Schedule | Manual processes delay request handling and reporting. | Estimated timeline 3–6 months (requirements → design → development → testing → deployment). | ✅ Achievable timeline

## ورقة2
Perfect 👍 Here’s a Cost–Benefit Analysis Table for the Tenant Maintenance Request System:
Cost–Benefit Analysis – Tenant Maintenance Request System
Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
Software | Development (in-house) or purchase of maintenance management system | $2,000 – $4,000 | Centralized request management reduces lost requests and delays. | $2,500 savings in administrative effort
Hardware / Hosting | Basic office devices, hosting, backup storage, and optional photo storage | $500 – $1,500 | Faster request processing; reliable access and backups. | $1,200 saved in staff workload
Training | Property manager and maintenance staff training sessions | $300 – $600 | Smooth transition and more efficient use of the system. | Higher productivity (≈ $800)
Maintenance | Annual software updates, bug fixes, security, and hosting support | $600 – $1,000 | Ensures system reliability, security, and continuous availability. | $1,300 saved from delays and downtime
Administration | Current manual follow-up, calls, paper forms, spreadsheets, and status inquiries | $800 annually | Reduced paperwork, phone follow-up, and manual record keeping. | $800 saved
Tenant Experience | Tenants spend time calling or asking for maintenance status | – | Online submission and status tracking improve transparency and satisfaction. | Intangible but high value
## Summary
Total Estimated Costs (first year): $4,200 – $7,900
Total Estimated Annual Benefits/Savings: approximately $6,600+
Payback Period: Within 1 year
Conclusion: The Tenant Maintenance Request System is economically feasible, with expected savings from reduced administrative work, faster request handling, fewer lost requests, and improved maintenance coordination.